## PRODUCT BACKLOG
ID | Feature | Priority | Sprint 1 | Sprint 2 | Sprint 3
1 | Create cooperation agreement(samenwerkingscontract) | M | x
2 | Make a GitHub project | M | x
3 | Visualize app | M | x
4 | Create a filter | W |  |  | x
5 | Create Buttons | M |  | x
6 | Create an interactive map | M |  | x
7 | Implement the Real Estate values in a database | M |  | x
8 | Implement the Real Estate values in the map | M |  | x
9 | Implement income per capita in a database | M |  | x
10 | Implement the income per capita in the Map | M |  | x
11 | Show the percentage the Real Estate values change from year to year in the Database | M |  | x
12 | Research Datasets | M | x
13 | Define recommendation function | M |  | x
14 | Input income function | M |  |  | x
15 | Fix the remaining bugs and glitches | M |  |  | x
16 | Show information about the different backgrounds in a neighbourhood | W |  |  | x
17 | Show information about sexuality in the neigbourhood | W |  |  | x
18 | Show the careers of the neighbourhood | W |  |  | x
19 | Show the average size of families in the neigbourhood | W |  |  | x
20 | Show the availability of facilities in the neigbourhood | W |  |  | x
. | . | . |  | .

## SPRINT 1 BACKLOG
SPRINT 1 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
1 | As a team we want a cooperation agreement to ensure we are able to punish the naughty | M | 0.5 | Write and agree on the contract | - when everyone has signed the contract. - When all the neccesary rules and agreements are put into the cooperation agreement
2 | As a team we want to use GitHub to be able to track what everyone is doing | M | 2 | Set up repository and connect to computers | - When everyone is able to use the GitHub app
3 | As a team we need to know what the application will look like to be able to develop it and plan it out | M | 2 | -Sketch -Make a digital drawing | - A clear sketch of all functions and buttons in the app - Digital
12 | As developers we need to research the databases to think of an idea | M | 1 | Look at the open data websites, mindstorm, pick idea | - When everyone agreed on the idea - When the idea is clear
EXAMPLE
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
1 | As a player I want to start the game from the menu, so that I can play it. | M | [1] | - Find a proper button texture - Load and display button texture on run - When clicked on screen, retrieve position - If clicked on start button, init game | - Button displayed on menu screen - Button has a reasonable size compared to screen dimension - Clicks not on the button area have no effect on game start - Clicks on the button area make the screen change (to init phase)
1 | As a player I want to quit the program from the menu, so that I can stop playing. | M | [1] | - Find a proper button texture - Load and display button texture on run - When clicked on screen, retrieve position - If clicked on exit button, quit program | - Button displayed on menu screen - Button has a reasonable size compared to screen dimension - Clicks not on the button area have no effect on quit program - Clicks on the button area make the program quit

## SPRINT 2 BACKLOG
SPRINT 2 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
5 | As a developer I want the app to have buttons to give the app actions and making it dynamic | M | 0.5 | - Create buttons that interact with the app | All buttons connect correctly to the functions of the buttons.
6 | As a user I want to see the data in an interactive map so I can easily see for which neighborhood each set of data applies | M | 20 | - Implement map - Implement options that change the map | if the map changes based on the input of your budget.
7 | As a developer I want to have a database with the values of the real estate each year in each neighborhood so I can implement them in the interactive map | M | 2 | - Write the tables for the database - Insert data into the database | When the database works, by testing the database. This is tested by writing queries that interact with the database.
8 | As a user I want see the average value of the real estate in a neighborhood so I can see which neighborhood fits best with my budget | M | 3 | - Create real estate groups - Assign color to a real estate group - Show the information on the map according to database | The neightbourhood best suited compared to the budget will gain a different visual aspect than from the rest.
9 | As a developer I want to have a database with the information about the average income for each neighborhood so I can implement these in the interactive map | M | 2 | - Write the tables for the database - Insert data into the database | The data that's shown for a neightboorhood matches correctly with the data in the database and datasets.
10 | As a user I want see the the average income in a neighborhood so I can find the neighborhood where people have a similiar income as me | M | 3 | - Create search function | The data of the average income is coorect in relation to the database and the datasets.
11 | As a user I want to know how much the value of the real estate in a neighborhood changes each year so it can be determined if I will make a profit or a loss in the long-term | M | 8 | - Writing a function that calculates the percentage relative to the previous year | The data of the real estate value is visual in the program and matches the database correctly.
13 | As as user I want to see in which neighborhood the real estate fits best with me | M | 5 | - Write a function that uses the value of the input and compares it with the income in the neighourhoods | The program will visually show which neightborhood has the best real estate compared to the requirements. ( budget , filter)
EXAMPLE
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
1 | As a player I want to start the game from the menu, so that I can play it. | M | [1] | - Find a proper button texture - Load and display button texture on run - When clicked on screen, retrieve position - If clicked on start button, init game | - Button displayed on menu screen - Button has a reasonable size compared to screen dimension - Clicks not on the button area have no effect on game start - Clicks on the button area make the screen change (to init phase)
1 | As a player I want to quit the program from the menu, so that I can stop playing. | M | [1] | - Find a proper button texture - Load and display button texture on run - When clicked on screen, retrieve position - If clicked on exit button, quit program | - Button displayed on menu screen - Button has a reasonable size compared to screen dimension - Clicks not on the button area have no effect on quit program - Clicks on the button area make the program quit

## SPRINT 3 BACKLOG
SPRINT 3 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
4 | As a user I want to be able to use a filter so I can get to the functions I need | M | 5 | - Use a query that filters - Implement filter in the app | Menu is done when the menu has implemented all the buttons and functions.
14 | As a user I want to be able to input my budget so the program will show me relevant information | M | 5 | - Make input field for income - Change colors for the income | Being able to input a big number and the colors change relative to the number.
15 | As a user I do not want to have bugs in the app so I can use the app to its full potention | M | 8 | - Locate bugs - Fix the bugs with the team | The IE gives no errors back and the program works like it has to, so no logical errors.
19 | As a user I want the program to show me the average family size in the neighbourhood so I know if the place fits preferences | W | 2 | - Write the tables for the database - Insert data into the database | When the database works, by testing the database. This is tested by writing queries that interact with the database.
EXAMPLE
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
1 | As a player I want to start the game from the menu, so that I can play it. | M | [1] | - Find a proper button texture - Load and display button texture on run - When clicked on screen, retrieve position - If clicked on start button, init game | - Button displayed on menu screen - Button has a reasonable size compared to screen dimension - Clicks not on the button area have no effect on game start - Clicks on the button area make the screen change (to init phase)
1 | As a player I want to quit the program from the menu, so that I can stop playing. | M | [1] | - Find a proper button texture - Load and display button texture on run - When clicked on screen, retrieve position - If clicked on exit button, quit program | - Button displayed on menu screen - Button has a reasonable size compared to screen dimension - Clicks not on the button area have no effect on quit program - Clicks on the button area make the program quit

## PB
PRODUCT BACKLOG ( EXAMPLE )
ID | Feature | Category | Priority | Sprint 1 | Sprint 2 | Sprint 3
0 | Display menu screen on program start | Menu | M
1 | Menu with "start game","Highscores","Load Game", "Options","Help", "exit" buttons | Menu | M
2 | Show the rules of the game when needed by user | Menu or Turn | M
3 | Screen to select the number of players | Init | M
4 | Display game board | Init | M
5 | Place all pawns on first tile | Init | M
6 | Display "exit" button | Init and Turn | M
7 | Display which player is playing the current turn | Turn | M
8 | Current player can roll the dice and see the result | Turn | M
9 | Move the pawn of the player forward according to dice result | Turn | M
10 | Execute special actions (for example, go back to tile 1) according to the tile on which the player arrives | Turn | M
11 | Change current player after the end of the turn | Turn | M
12 | Show win screen if current player destroys enemy's ships | End | M
13 | "Go back to menu" button is displayed in the win screen | End | S
14 | Current player can pause and resume the game | Turn | S
15 | Produce sound for throw of a dice / moving pawn / win screen / special actions | Turn | C
16 | Display dice throw / moving pawn with an animation | Turn | C
17 | Menu extended with "settings" button (for example, containing screen resolution, audio volume, …) | Menu | C
18 | Possibility to select also computer players | Init | C
19 | Computer player is able to play the game | Turn | C
20 | Add some humour to the computer player | Turn | W
21 | Save current state of the game on a file | Turn | C
22 | Load a previously saved game state | Menu | C
23
24 | Make game playable by users sitting at different PCs (LAN multiplayer) | Menu and Turn | C
25 | Player is able to switch between Dutch and English | Game